## How to use
Instant run sheet
The Instant Framework (theinstantframework.com) by Falcra (falcratechnologies.com). Version 1.0, 8 Oct 2026. Licence: CC BY 4.0 (see the Licence tab).
What it is
Every step of an Instant engagement in order, from preparation to release: what to do next, who leads it, who helps, what to use, and what "done" looks like. It is for the Conductor and the Stage Manager (or your project manager) to follow and tick off.
How to use it
1. Delete the rows that don't apply (see the Applies column), or set them to "Not needed".
2. Put a name and a due date against each step. Long-lead steps in S0 come first, because they take weeks inside a large organisation.
3. Copy the S4 Build rows once for each Unit of Work, after the units are approved in S3. Add the unit to the step ID (for example S4-01-U3).
4. Update the Status as you go. The Summary tab shows the next step not yet done, and how many steps remain in each stage.
5. The Every session tab lists what happens at every Blitz session, from Frame to the last Bolt in the Blitz.
6. Record every sign-off in your sign-off register as well. This run sheet tracks the work; the register is the record.
What to use
"Guide" and "Practices" refer to the chapters of the Instant Guide and Instant Practices at theinstantframework.com. Free downloads named in the Use column are also there.
Columns
Who leads: the person who makes sure the step happens. With: who helps, decides or records. Done when: how you know it is finished. Sign-off: the gate or approval the step ends with, if any. Applies: always, or only in the situation named.
Status, Name, Due and Notes are yours to fill in.

## Summary
Summary (worked out from the Run sheet)
Next step
Who leads it
Use
Stage | Steps | Done or not needed | Remaining
S0 Prepare
S1 Frame
S2 Specify
S3 Design
S4 Build
S5 Prove
S6 Release and refine
Total

## Run sheet
ID | Stage | Step | Who leads | With | Use | Done when | Sign-off | Applies | Status | Name | Due | Notes
S0-01 | S0 Prepare | Agree the brief: what you want to build and why. | Challenger | Business owner | Guide, chapter 6 | Brief agreed |  | Always | Not started
S0-02 | S0 Prepare | Choose the crew option (A Combined, B Split, C Developer Conductor) and whether to add a Stage Manager. | Business owner | Challenger | Guide, chapter 7; Practices, chapter 1 | Crew named |  | Always | Not started
S0-03 | S0 Prepare | Choose the Blitz format, consecutive days or split sessions, and book every session (gaps of a week at most). | Business owner | Stage Manager | Guide, chapter 6 | Every session booked |  | Always | Not started
S0-04 | S0 Prepare | Collect your existing documentation, including earlier work such as BRDs, NFRs and ERDs, and sort it by stage. What belongs where: see S0 in the Guide. | Challenger | Your experts | Guide, chapter 8 | Every document assigned to a stage |  | Always | Not started
S0-05 | S0 Prepare | Gather your change-control and audit rules. | Challenger | Technical owner | Guide, chapter 6 | Rules gathered |  | Always | Not started
S0-06 | S0 Prepare | Write the security constraints package. | Security lead | Challenger | Practices, chapter 1 | Package written |  | If you want one | Not started
S0-07 | S0 Prepare | Agree the assurance approach and name the evidence pack signatories: a business owner and a technical owner. | Challenger | Business owner | Practices, chapter 3; Guide, chapter 9 | Both signatories named |  | Always | Not started
S0-08 | S0 Prepare | Arrange recording and transcription for every session, and get everyone's agreement. | Stage Manager | Challenger | Guide, chapter 9 | Agreement recorded |  | Always | Not started
S0-09 | S0 Prepare | Start the long-lead requests (listed under Preparation in the Guide). Filter the Jira backlog on its long-lead label. | Stage Manager | Roadie | Guide, chapter 6; Practices, chapter 2; Instant Jira backlog (free download) | Every long-lead request lodged |  | Always | Not started
S0-10 | S0 Prepare | Existing data: confirm the backup and request read-only database access. A direct connection is preferred; see Practices for why. | Stage Manager | Your database administrator | Practices, chapter 2 | Backup confirmed; access requested |  | If the application replaces or draws on a system that holds data | Not started
S0-11 | S0 Prepare | Set up the board: import the Jira backlog, delete what doesn't apply, and date the milestones from your governance calendar. | Stage Manager | Conductor | Practices, chapter 1; Instant Jira backlog (free download) | Board loaded and dated |  | If you use Jira | Not started
S0-12 | S0 Prepare | Set up the sign-off register, with every expected sign-off listed as pending. | Stage Manager | Conductor | Guide, chapter 8; Instant sign-off timeline (free download) | Every expected sign-off listed |  | Always | Not started
S0-13 | S0 Prepare | Complete the readiness checklist. | Challenger | Stage Manager | Guide, chapter 6 | Checklist complete | Ends S0 | Always | Not started
S1-01 | S1 Frame | Give the AI the brief and the business case or problem statement. | Conductor |  | Guide, chapter 8 | Documents given |  | Always | Not started
S1-02 | S1 Frame | Agree the Intent and scope, as set out under S1 in the Guide. | Conductor | The whole room | Guide, chapter 8 | Intent and scope drafted |  | Always | Not started
S1-03 | S1 Frame | Agree the triage policy for features nobody asked for: the default for each kind of addition. | Challenger | The whole room | Practices, chapter 3 | Policy agreed |  | Always | Not started
S1-04 | S1 Frame | The room approves the Intent and scope. Record it in the sign-off register. | Conductor | Stage Manager | Guide, chapter 8 | Approval recorded | Stage approval | Always | Not started
S2-01 | S2 Specify | Give the AI the documents sorted to this stage (listed under S2 in the Guide). | Conductor | Challenger, who selects them | Guide, chapter 8 | Documents given |  | Always | Not started
S2-02 | S2 Specify | Choose requirements or user stories. | Business owner | Challenger | Practices, chapter 1 | Choice recorded |  | Always | Not started
S2-03 | S2 Specify | Draft the requirements or user stories with the AI and review them in the room. | Your experts | Challenger tests; Conductor drives | Guide, chapter 8 | Reviewed in the room |  | Always | Not started
S2-04 | S2 Specify | Capture the critical rules as decision tables. The AI drafts them; your experts check them. | Conductor | Your experts | Practices, chapter 3 | Every critical rule in a decision table |  | Always | Not started
S2-05 | S2 Specify | Give each part of the application a risk tier. The AI proposes; your experts and business owner decide; the Challenger tests the reasons. | Your experts and business owner | Conductor records | Practices, chapter 1; Instant risk tier register (free download) | Every part has a tier |  | Always | Not started
S2-06 | S2 Specify | Choose the data architecture level, after the six questions are put to the room. | Business owner | Conductor | Practices, chapter 1 | Level chosen |  | Always | Not started
S2-07 | S2 Specify | Agree the non-functional requirements: your standards first, and the ten questions put to the business owners. | Conductor | Business owner | Practices, chapter 2 | Targets agreed |  | Always | Not started
S2-08 | S2 Specify | Your experts and testers begin writing the acceptance tests. | Your experts and testers |  | Practices, chapter 3 | Tests started |  | Always | Not started
S2-09 | S2 Specify | Gate G1, Spec agreed: the business approves the requirements or user stories in the room. Record it. | Business owner | Stage Manager records | Guide, chapter 8 | G1 recorded | G1 | Always | Not started
S3-01 | S3 Design | Give the AI the documents sorted to this stage (listed under S3 in the Guide). | Conductor | Roadie, for technical material | Guide, chapter 8 | Documents given |  | Always | Not started
S3-02 | S3 Design | Design the architecture, components and screen mockups. | Conductor | Your experts | Guide, chapter 8 | Design and mockups approved |  | Always | Not started
S3-03 | S3 Design | Produce the build-readiness spreadsheet: every requirement sorted A Ready, B Code buildable, C Cannot be built, D Source unverified. | Conductor | Business owner decides each row | Practices, chapter 4 | No row awaiting a decision |  | Always | Not started
S3-04 | S3 Design | Approve the Units of Work, Bolts and build order that the AI proposes. | Conductor | The whole room | Guide, chapter 8 | Units and order approved |  | Always | Not started
S3-05 | S3 Design | Set up Git: a branch per Unit of Work, squash on merge, branch protection, and the pull request template. | Roadie | Conductor | Practices, chapter 3; Instant pull request template (free download) | A direct push to main is refused |  | Always | Not started
S3-06 | S3 Design | Set up the automated checks, and show each one failing on a deliberately broken case. | Roadie |  | Practices, chapter 3 | Every check's failure test recorded |  | Always | Not started
S3-07 | S3 Design | Add one tracker item per Unit of Work, plus one Refinements item per unit. | Stage Manager | Conductor | Practices, chapter 3 | Board shows every unit |  | If you use Jira or another tracker | Not started
S3-08 | S3 Design | Gate G2, Ready to build: the build-readiness spreadsheet, risk tier register (no tier still proposed) and data architecture level are done. Record it. | Conductor and business owner | Stage Manager records | Guide, chapter 8 | G2 recorded | G2 | Always | Not started
S4-01 | S4 Build | Give the AI the unit's decisions, decision tables and mockups. | Conductor |  | Guide, chapter 8 | Documents given |  | Every unit | Not started
S4-02 | S4 Build | Build Bolt by Bolt. Your experts decide what appears on screen; Tweaks are made on the spot; commits are saved at checkpoints. | Conductor | Your experts | Practices, chapter 3 | Unit built |  | Every unit | Not started
S4-03 | S4 Build | Treat any small request that changes behaviour as a rule, not a Tweak: record it as a decision. | Conductor | Scorekeeper | Practices, chapter 3 | Every rule recorded |  | Every unit | Not started
S4-04 | S4 Build | Explain-back: the AI explains each critical module in plain English; an expert confirms or corrects it. | Conductor | Your experts | Practices, chapter 3 | Explain-backs signed |  | Units with critical logic | Not started
S4-05 | S4 Build | Raise one pull request for the unit, with its intent summary filled in from the template. | Conductor |  | Practices, chapter 3; Instant pull request template (free download) | Pull request raised |  | Every unit | Not started
S4-06 | S4 Build | Independent AI review; resolve every critical finding. | Conductor | Roadie oversees | Practices, chapter 3 | Findings resolved |  | Every unit | Not started
S4-07 | S4 Build | Human review by risk tier, by a named approver. | Named reviewer | Roadie oversees | Practices, chapter 3 | Approval given |  | Every unit | Not started
S4-08 | S4 Build | Answer reviewers' questions on the pull request: at the end of each Bolt in the Blitz, at least daily after it. | Conductor | Scorekeeper, for business questions | Practices, chapter 3 | No open questions |  | When questions are raised | Not started
S4-09 | S4 Build | Check the unit's feature inventory: triage anything nobody asked for against the agreed policy. | Your experts | Conductor; Scorekeeper records | Practices, chapter 3 | Nothing unrequested left undecided |  | Every unit | Not started
S4-10 | S4 Build | Gate G3, Unit accepted: tests pass, AI findings resolved, human review done, feature inventory checked. Record it. | Named reviewer | Stage Manager records | Guide, chapter 8 | G3 recorded for the unit | G3 | Every unit | Not started
S5-01 | S5 Prove | Give the AI your test standards and change-control evidence requirements. | Conductor |  | Guide, chapter 8 | Documents given |  | Always | Not started
S5-02 | S5 Prove | Settle every feature nobody asked for before user acceptance testing starts. | Your experts | Conductor | Practices, chapter 3 | Every item decided |  | Always | Not started
S5-03 | S5 Prove | Run the acceptance tests and user acceptance testing. | Your experts and testers |  | Guide, chapter 8 | Tests passed |  | Always | Not started
S5-04 | S5 Prove | Produce the traceability matrix, checked in both directions. | Conductor |  | Guide, chapter 8; Practices, chapter 3 | Matrix complete in both directions |  | Always | Not started
S5-05 | S5 Prove | Rehearse the migration until clean, and reconcile counts, totals and samples. | Conductor and Roadie | Your database administrator and data owners | Practices, chapter 2 | Reconciliation passed |  | If there is existing data | Not started
S5-06 | S5 Prove | Put the production safety nets in place: the audit level chosen, alerts, and hard limits on critical values. | Technical owner | Roadie | Practices, chapter 3 | Safety nets in place |  | Always | Not started
S5-07 | S5 Prove | Assemble the evidence pack. | Business owner and technical owner | Conductor | Practices, chapter 3 | Pack complete |  | Always | Not started
S5-08 | S5 Prove | Gate G4, Go-live: your business owner and technical owner sign the evidence pack. Record it. | Business owner and technical owner | Stage Manager records | Guide, chapter 8 | G4 recorded | G4 | Always | Not started
S6-01 | S6 Release and refine | Give the AI your release, change and operational handover requirements. | Conductor | Roadie | Guide, chapter 8 | Documents given |  | Always | Not started
S6-02 | S6 Release and refine | Release through Test and UAT to production, with the change request, cutover and hypercare coordinated. | Technical owner and operations | Stage Manager | Guide, chapter 8; Guide, chapter 7 | In production |  | Always | Not started
S6-03 | S6 Release and refine | Produce the Information Model and the Data Model. | Conductor | Technical owner reviews | Practices, chapter 1; Instant Information Model (free download); Instant Data Model (free download) | Both reviewed |  | Always | Not started
S6-04 | S6 Release and refine | One or two experts refine the build; what they learn feeds the next Frame. | Your experts | Conductor | Guide, chapter 6 | Refinements logged |  | Always | Not started
S6-05 | S6 Release and refine | Keep monitoring and sampling, and give each significant release its own evidence. | Technical owner |  | Practices, chapter 3 | Ongoing |  | After go-live | Not started
S6-06 | S6 Release and refine | The release is approved under your change process. Record it. | Technical owner | Stage Manager records | Guide, chapter 8 | Approval recorded | Ends S6 | Always | Not started

## Every session
ID | Stage | Step | Who leads | With | Use | Done when | Sign-off | Applies | Status | Name | Due | Notes
EV-01 | Every session | Start recording and transcription. In a split Blitz, the Conductor confirms which stage the AI build tool is at. | Conductor | Stage Manager | Guide, chapter 6 | Recording on |  | Every session | Not started
EV-02 | Every session | Record your experts' feedback as it happens; note anything the room can't settle for the AI later. | Scorekeeper |  | Guide, chapter 7 | Feedback record up to date |  | Every session | Not started
EV-03 | Every session | Short wrap-up at the end of each day. | Stage Manager | Crew | Guide, chapter 7 | Wrap-up held |  | If you have a Stage Manager | Not started
EV-04 | Every session | Save the transcript and cross-check it against the Scorekeeper's feedback record. | Scorekeeper | Conductor | Guide, chapter 6 | Transcript saved and checked |  | Every session | Not started
EV-05 | Every session | Split Blitz: settle the open questions between sessions, so nothing waits at the next one. | Stage Manager | Challenger | Guide, chapter 6 | No question left waiting |  | Split Blitz only | Not started

## Licence
© 2026 What Did I Buy Online Pty Ltd, trading as Falcra. This run sheet is licensed under the Creative Commons Attribution 4.0 International licence (CC BY 4.0), https://creativecommons.org/licenses/by/4.0/.
You may copy, change and share it, including commercially, provided you credit Falcra, link to the original and to the licence, and say if you changed it. A changed version must not suggest that Falcra made or endorses it.
Suggested credit: "Based on the Instant run sheet from The Instant Framework (theinstantframework.com) by Falcra (falcratechnologies.com), CC BY 4.0." Drop "Based on" if you share it unchanged.
Run sheets you fill in with it are yours. They don't need to carry the credit.